## Sheet1
Legend:
Completed
InProgress
Yet to Start
Activities: | Responsible person | Status | Activity diagrams and Use case descriptions | Owner
1. Add use case diagram for Admin | Sachin | Done | Client Sign Up | Sachin
Also split use case diagrams - 3 | Sachin | Done | Nutritionist Sign up | Sachin
2. Add FP calculation | Sudarshan | Done | Nutritionist Search | Sachin
3. Create project plan | Sachin | Done | Book appointment with nutritionist | Sachin
4. Write use case descriptions in tabular form | All | DOne | View Recipe book | Sachin
4. Update class diagram - 2 | Kunal | Done | View Food dictionary | Sudarshan
5. Write ER diagram - 1 | Kunal | Done | Give Rating to Nutritionist | Sudarshan
6. Remaining activity diagrams - 15 | All | Done | View Client Health History | Sudarshan
6. Write State diagram - 3 | Akhil | Done | Create Food dictionary | Sudarshan
7. Package diagram - 1 | Kunal | Done | Create Recipe Book | Sudarshan
8. Deployment diagram - 1 | Kunal | Done | Create Diet Plan | Akhil
9. Data Flow Diagram - 1 | Akhil | Done | Create Custom Diet Plan | Akhil
10. Source code and sql files | Sudarshan |  | Adding user activity | Akhil
11. Test cases list | Sudarshan | Done | Adding food consumption | Akhil
12. Basic prototype with 10 use cases | Kunal, Nikhil |  | Generating activity report for specified period | Akhil
13 |  |  | Rate Nutritionist | Kunal
|  |  | Delete client | Kunal