## Sheet1
ID | Epic | Owner | Activity | Outcome | Estimate | Priority | Notes
1 | Local | Indivdual Team member | Install a local development Environment | setup local Typo3 environment | 2 | 10 | Linux, DDEV,Docker,Git,PHPStorm,Source Tree
2 | Local | Indivdual Team member | setup a local Typo3 Environment | get an overview of Typo3 features | 3 | 10 | DDEV, Composer, Inroduction package,TYPO3 v9 LTS
3 | Local | Indivdual Team member | get detailed insight into TYPO3s extensibility and customization | adjust the base system for own demands | 10 | 9 | Hands-on with introduction package and customizing
4 | Concept | Team | Concept definition and Planning of NutriSpec | Concept description and list of use cases | 2 | 9
5 | Design | Team | Designing Wirefeames | Wireframes of how the actual web page looks | 1 | 8 | Balsamiq tool exploration and wireframe construction
6 | Design | Team | Logo design | Design a Logo for NutriSpec | 1 | 8
7 | Design | Team | Domain Modelling and Controllers design | TYPO3 Domain Model and Class definitions and diagrams | 2 | 8
8 | Implementation | Team | Installing Bootstrap package and customize | Customized bootstrap for NutriSpec | 3 | 8
9 | Implementation | Team | ExtBase implementation for NutriSpec | Customized ExtBase for NutriSpec | 3 | 9 | User Login part removed
10 | Implementation | Team | Custom human readable routing URL's for NutriSpec | Simple URL for NutriSPec | 1 | 9
11 | Testing | Team | Manual Tests | Verification of Page navigations | 1 | 9 | Defining test cases and executions
12 | Testing | Team | Automation tests | Verification of page inputs and outputs | 2 | 9 | This includes:Configuring Automation framework and tools, implementation of test suits and execution
13 | Deployment | Team | Deploy website | Publicly available web url | 1 | 9 | Used web server host provided in the course